## Hire Register
Equipment Hire Register
Track what is on hire, where it is, what it costs and whether the off-hire has been confirmed.
Cost figures are estimates. Always check agreed rates, chargeable days and off-hire terms with the supplier.
Status | Equipment | Site | Supplier | Hire reference / PO | Start date | Expected end date | Calendar days on hire | Agreed rate | Rate basis | Chargeable days per week | Estimated weekly cost | Still needed? | Off-hire requested | Supplier confirmation / reference | Confirmed off-hire date | Collection date | Notes
On hire | Scissor lift | Example Site | Example Supplier | EX-1001 | 2026-09-01 | 2026-09-29 |  | 85 | Daily | 7 |  | Yes |  |  |  |  | EXAMPLE – delete this row
Ready to come off | Dumper | Riverside Example Works | Example Supplier | EX-1002 | 2026-08-18 | 2026-09-19 |  | 420 | Weekly | 6 |  | No |  |  |  |  | EXAMPLE – delete this row
Off-hire requested | Welfare unit | Example Site | Example Supplier | EX-1003 | 2026-08-04 | 2026-09-11 |  | 145 | Daily | 5 |  | No | 2026-09-16 |  |  |  | EXAMPLE – delete this row
Formulas:
Calendar days on hire = IF([Start date]="","",MAX(0,IF([Collection date]="",TODAY(),[Collection date])-[Start date]+1))

## Instructions
How to use this equipment hire register
1. Add every item currently on hire.
2. Record the site, supplier, start date, expected end date and agreed rate.
3. Review the register with the person responsible for each site.
4. Mark anything no longer needed as ready to come off.
5. Record when the off-hire request was sent.
6. Add the supplier’s confirmation or off-hire reference.
7. Keep the item visible until collection is complete.
8. Review the register at least weekly.
An expected end date does not automatically end a hire. Follow the supplier’s off-hire process and retain their confirmation or reference.
Hire charging arrangements vary. Estimated costs in this template are for visibility and should be checked against the supplier’s agreed rates and terms.
Turn this spreadsheet into a live hire process with What’s On Hire
Calendar days on hire count from the start date to the collection date, or to today if collection has not been recorded. They are not chargeable days.
Actual invoices depend on supplier terms, minimum hire periods, holidays, weekends and agreed charging arrangements.

## Lists (hidden)
Status | Rate basis | Still needed? | Chargeable days
On hire | Daily | Yes | 5
Review needed | Weekly | No | 6
Ready to come off | Monthly | Review | 7
Off-hire requested
Supplier confirmed
Awaiting collection
Collected / closed